## Dashboard
Job Costing Dashboard
Sample carpentry business · Jul–Oct 2026 · Sample project, placeholder data
Active jobs | Quoted value (all jobs) | Actual cost to date | Gross profit, finished jobs | Avg margin, finished jobs | Jobs over budget | Jobs at risk
4 | 117330 | 67675.5 | 14663 | 24.41% | 3 | 1
Job | Status | Quote | Budget cost | Actual cost | Margin % | Budget used % | Cost by category | Amount
J-2601 Deck | Invoiced | 11580 | 8888 | 8555 | 26.12% | 96.25% | Labour | 19458
J-2602 Pergola | Invoiced | 7860 | 5580 | 5890 | 25.06% | 105.6% | Materials | 39643.67
J-2603 Kitchen joinery | Complete | 21610 | 15832 | 17749.5 | 17.86% | 112.1% | Subcontractor | 2282.3
J-2604 Built-in wardrobes | Complete | 8890 | 6316 | 5637.5 | 36.59% | 89.26% | Equipment hire | 2726.84
J-2605 Fencing | Complete | 5400 | 3860 | 3729 | 30.94% | 96.61% | Travel & parking | 1102.38
J-2606 Bathroom vanity | Complete | 3610 | 2656 | 3090.5 | 14.39% | 116.4% | Waste removal | 2462.31
J-2607 Repairs | Complete | 1130 | 870 | 765.5 | 32.26% | 87.99%
J-2608 Deck | In progress | 14300 | 10424 | 9393 | 34.31% | 90.11% | Hours by staff | Hours
J-2609 Built-in wardrobes | In progress | 9670 | 6984 | 3912.5 | 59.54% | 56.02% | Sam R. (lead carpenter) | 117
J-2610 Kitchen joinery | In progress | 19520 | 13896 | 8953 | 54.13% | 64.43% | Ari K. (carpenter) | 148.5
J-2611 Pergola | Booked | 8110 | 5948 | 0 |  | 0% | Jo P. (apprentice) | 97
J-2612 Fencing | Quoted | 5650 | 4328 | 0 |  | 0% | Dev M. (labourer) | 103.5
Checks | 8 of 8

## Jobs
Job ID | Client | Job type | Start date | Status | Quote (ex. extras) | Budget labour hrs | Budget labour cost | Budget materials & other | Budget total cost | Actual hrs | Actual labour cost | Actual materials & other | Actual total cost | Gross profit | Margin % | Budget used % | Flag | Yellow cells are inputs; everything else is calculated.
J-2601 | Larchmere household | Deck | 2026-07-06 | Invoiced | 11580 | 64 | 2688 | 6200 | 8888 | 62.5 | 2541 | 6014 | 8555 | 3025 | 26.12% | 96.25% | On track
J-2602 | Ottercombe Yoga | Pergola | 2026-07-13 | Invoiced | 7860 | 40 | 1680 | 3900 | 5580 | 41 | 1912 | 3978 | 5890 | 1970 | 25.06% | 105.6% | Over budget
J-2603 | Saltreed Barbers | Kitchen joinery | 2026-07-20 | Complete | 21610 | 96 | 4032 | 11800 | 15832 | 109.5 | 4297.5 | 13452 | 17749.5 | 3860.5 | 17.86% | 112.1% | Over budget
J-2604 | Fenwick Lane Books | Built-in wardrobes | 2026-07-27 | Complete | 8890 | 48 | 2016 | 4300 | 6316 | 44 | 1724.5 | 3913 | 5637.5 | 3252.5 | 36.59% | 89.26% | On track
J-2605 | Sample Café | Fencing | 2026-08-03 | Complete | 5400 | 30 | 1260 | 2600 | 3860 | 26.5 | 1441 | 2288 | 3729 | 1671 | 30.94% | 96.61% | On track
J-2606 | Duskwater Gallery | Bathroom vanity | 2026-08-10 | Complete | 3610 | 18 | 756 | 1900 | 2656 | 22 | 791.5 | 2299 | 3090.5 | 519.5 | 14.39% | 116.4% | Over budget
J-2607 | Brackwhistle Kitchen | Repairs | 2026-08-17 | Complete | 1130 | 10 | 420 | 450 | 870 | 9.5 | 338 | 427.5 | 765.5 | 364.5 | 32.26% | 87.99% | On track
J-2608 | Quellbrook Physio | Deck | 2026-08-24 | In progress | 14300 | 72 | 3024 | 7400 | 10424 | 67 | 2511 | 6882 | 9393 | 4907 | 34.31% | 90.11% | At risk
J-2609 | Pellicott household | Built-in wardrobes | 2026-08-31 | In progress | 9670 | 52 | 2184 | 4800 | 6984 | 29 | 1272.5 | 2640 | 3912.5 | 5757.5 | 59.54% | 56.02% | On track
J-2610 | Corrowind household | Kitchen joinery | 2026-09-07 | In progress | 19520 | 88 | 3696 | 10200 | 13896 | 55 | 2629 | 6324 | 8953 | 10567 | 54.13% | 64.43% | On track
J-2611 | Wrenfeather Studio | Pergola | 2026-09-14 | Booked | 8110 | 44 | 1848 | 4100 | 5948 | 0 | 0 | 0 | 0 | 0 |  | 0% | Not started
J-2612 | Marrowbine Bakes | Fencing | 2026-09-21 | Quoted | 5650 | 34 | 1428 | 2900 | 4328 | 0 | 0 | 0 | 0 | 0 |  | 0% | Not started

## Timesheet
Date | Job ID | Staff | Hours | Cost rate /hr | Labour cost
2026-07-06 | J-2601 | Jo P. (apprentice) | 7.5 | 27 | 202.5
2026-07-07 | J-2601 | Ari K. (carpenter) | 8 | 44 | 352
2026-07-08 | J-2601 | Dev M. (labourer) | 4 | 34 | 136
2026-07-09 | J-2601 | Jo P. (apprentice) | 4 | 27 | 108
2026-07-10 | J-2601 | Dev M. (labourer) | 7.5 | 34 | 255
2026-07-13 | J-2601 | Ari K. (carpenter) | 8 | 44 | 352
2026-07-13 | J-2602 | Ari K. (carpenter) | 4 | 44 | 176
2026-07-14 | J-2601 | Ari K. (carpenter) | 8 | 44 | 352
2026-07-14 | J-2602 | Sam R. (lead carpenter) | 6 | 58 | 348
2026-07-15 | J-2601 | Sam R. (lead carpenter) | 4 | 58 | 232
2026-07-15 | J-2602 | Ari K. (carpenter) | 4 | 44 | 176
2026-07-16 | J-2601 | Sam R. (lead carpenter) | 7.5 | 58 | 435
2026-07-16 | J-2602 | Sam R. (lead carpenter) | 6 | 58 | 348
2026-07-17 | J-2601 | Jo P. (apprentice) | 3.5 | 27 | 94.5
2026-07-17 | J-2602 | Ari K. (carpenter) | 6 | 44 | 264
2026-07-20 | J-2601 | Ari K. (carpenter) | 0.5 | 44 | 22
2026-07-20 | J-2602 | Ari K. (carpenter) | 8 | 44 | 352
2026-07-20 | J-2603 | Jo P. (apprentice) | 6 | 27 | 162
2026-07-21 | J-2602 | Dev M. (labourer) | 6 | 34 | 204
2026-07-21 | J-2603 | Ari K. (carpenter) | 8 | 44 | 352
2026-07-22 | J-2602 | Ari K. (carpenter) | 1 | 44 | 44
2026-07-22 | J-2603 | Dev M. (labourer) | 8 | 34 | 272
2026-07-23 | J-2603 | Jo P. (apprentice) | 8 | 27 | 216
2026-07-24 | J-2603 | Ari K. (carpenter) | 7.5 | 44 | 330
2026-07-27 | J-2603 | Jo P. (apprentice) | 7.5 | 27 | 202.5
2026-07-27 | J-2604 | Sam R. (lead carpenter) | 8 | 58 | 464
2026-07-28 | J-2603 | Dev M. (labourer) | 7.5 | 34 | 255
2026-07-28 | J-2604 | Jo P. (apprentice) | 8 | 27 | 216
2026-07-29 | J-2603 | Jo P. (apprentice) | 4 | 27 | 108
2026-07-29 | J-2604 | Ari K. (carpenter) | 8 | 44 | 352
2026-07-30 | J-2603 | Sam R. (lead carpenter) | 7.5 | 58 | 435
2026-07-30 | J-2604 | Dev M. (labourer) | 6 | 34 | 204
2026-07-31 | J-2603 | Sam R. (lead carpenter) | 6 | 58 | 348
2026-07-31 | J-2604 | Ari K. (carpenter) | 4 | 44 | 176
2026-08-03 | J-2603 | Ari K. (carpenter) | 4 | 44 | 176
2026-08-03 | J-2604 | Jo P. (apprentice) | 7.5 | 27 | 202.5
2026-08-03 | J-2605 | Ari K. (carpenter) | 6 | 44 | 264
2026-08-04 | J-2603 | Ari K. (carpenter) | 6 | 44 | 264
2026-08-04 | J-2604 | Ari K. (carpenter) | 2 | 44 | 88
2026-08-04 | J-2605 | Sam R. (lead carpenter) | 8 | 58 | 464
2026-08-05 | J-2603 | Jo P. (apprentice) | 6 | 27 | 162
2026-08-05 | J-2604 | Ari K. (carpenter) | 0.5 | 44 | 22
2026-08-05 | J-2605 | Sam R. (lead carpenter) | 6 | 58 | 348
2026-08-06 | J-2603 | Ari K. (carpenter) | 8 | 44 | 352
2026-08-06 | J-2605 | Sam R. (lead carpenter) | 6 | 58 | 348
2026-08-07 | J-2603 | Sam R. (lead carpenter) | 4 | 58 | 232
2026-08-07 | J-2605 | Dev M. (labourer) | 0.5 | 34 | 17
2026-08-10 | J-2603 | Ari K. (carpenter) | 4 | 44 | 176
2026-08-10 | J-2606 | Dev M. (labourer) | 8 | 34 | 272
2026-08-11 | J-2603 | Dev M. (labourer) | 7.5 | 34 | 255
2026-08-11 | J-2606 | Jo P. (apprentice) | 7.5 | 27 | 202.5
2026-08-12 | J-2606 | Sam R. (lead carpenter) | 4 | 58 | 232
2026-08-13 | J-2606 | Dev M. (labourer) | 2.5 | 34 | 85
2026-08-17 | J-2607 | Dev M. (labourer) | 8 | 34 | 272
2026-08-18 | J-2607 | Ari K. (carpenter) | 1.5 | 44 | 66
2026-08-24 | J-2608 | Sam R. (lead carpenter) | 4 | 58 | 232
2026-08-25 | J-2608 | Jo P. (apprentice) | 6 | 27 | 162
2026-08-26 | J-2608 | Ari K. (carpenter) | 4 | 44 | 176
2026-08-27 | J-2608 | Ari K. (carpenter) | 6 | 44 | 264
2026-08-28 | J-2608 | Sam R. (lead carpenter) | 6 | 58 | 348
2026-08-31 | J-2608 | Dev M. (labourer) | 7.5 | 34 | 255
2026-08-31 | J-2609 | Ari K. (carpenter) | 8 | 44 | 352
2026-09-01 | J-2608 | Dev M. (labourer) | 8 | 34 | 272
2026-09-01 | J-2609 | Jo P. (apprentice) | 4 | 27 | 108
2026-09-02 | J-2608 | Ari K. (carpenter) | 4 | 44 | 176
2026-09-02 | J-2609 | Dev M. (labourer) | 4 | 34 | 136
2026-09-03 | J-2608 | Jo P. (apprentice) | 7.5 | 27 | 202.5
2026-09-03 | J-2609 | Sam R. (lead carpenter) | 6 | 58 | 348
2026-09-04 | J-2608 | Jo P. (apprentice) | 7.5 | 27 | 202.5
2026-09-04 | J-2609 | Sam R. (lead carpenter) | 4 | 58 | 232
2026-09-07 | J-2608 | Dev M. (labourer) | 4 | 34 | 136
2026-09-07 | J-2609 | Jo P. (apprentice) | 2.5 | 27 | 67.5
2026-09-07 | J-2610 | Ari K. (carpenter) | 7.5 | 44 | 330
2026-09-08 | J-2608 | Dev M. (labourer) | 2.5 | 34 | 85
2026-09-08 | J-2609 | Sam R. (lead carpenter) | 0.5 | 58 | 29
2026-09-08 | J-2610 | Sam R. (lead carpenter) | 8 | 58 | 464
2026-09-09 | J-2610 | Dev M. (labourer) | 4 | 34 | 136
2026-09-10 | J-2610 | Sam R. (lead carpenter) | 7.5 | 58 | 435
2026-09-11 | J-2610 | Dev M. (labourer) | 8 | 34 | 272
2026-09-14 | J-2610 | Sam R. (lead carpenter) | 7.5 | 58 | 435
2026-09-15 | J-2610 | Ari K. (carpenter) | 8 | 44 | 352
2026-09-16 | J-2610 | Ari K. (carpenter) | 4 | 44 | 176
2026-09-17 | J-2610 | Sam R. (lead carpenter) | 0.5 | 58 | 29

## Costs
Date | Job ID | Category | Supplier | Description | Amount
2026-07-06 | J-2601 | Waste removal | Skip-it Bins | Waste removal for deck | 567.18
2026-07-06 | J-2601 | Equipment hire | Hirepoint | Equipment hire for deck | 461.87
2026-07-06 | J-2601 | Materials | Bayside Board Co | Materials for deck | 185.37
2026-07-07 | J-2601 | Materials | Bayside Board Co | Materials for deck | 944.56
2026-07-08 | J-2601 | Materials | Timberline Supplies | Materials for deck | 1280.21
2026-07-08 | J-2601 | Materials | Hardwarehouse | Materials for deck | 840.52
2026-07-10 | J-2601 | Materials | Hardwarehouse | Materials for deck | 1271.64
2026-07-12 | J-2601 | Materials | Bayside Board Co | Materials for deck | 462.65
2026-07-13 | J-2602 | Equipment hire | Hirepoint | Equipment hire for pergola | 205.61
2026-07-15 | J-2602 | Subcontractor | Spark Lane Electrical | Subcontractor for pergola | 415.37
2026-07-18 | J-2602 | Materials | Hardwarehouse | Materials for pergola | 1770.81
2026-07-20 | J-2602 | Equipment hire | Hirepoint | Equipment hire for pergola | 681.11
2026-07-20 | J-2603 | Materials | Bayside Board Co | Materials for kitchen joinery | 991.32
2026-07-22 | J-2603 | Materials | Hardwarehouse | Materials for kitchen joinery | 1002.96
2026-07-23 | J-2602 | Equipment hire | Hirepoint | Equipment hire for pergola | 325.64
2026-07-23 | J-2603 | Materials | Bayside Board Co | Materials for kitchen joinery | 1685.95
2026-07-23 | J-2603 | Materials | Bayside Board Co | Materials for kitchen joinery | 1500.18
2026-07-23 | J-2603 | Materials | Bayside Board Co | Materials for kitchen joinery | 1120.07
2026-07-25 | J-2602 | Materials | Timberline Supplies | Materials for pergola | 579.46
2026-07-26 | J-2603 | Materials | Bayside Board Co | Materials for kitchen joinery | 756.98
2026-07-26 | J-2603 | Materials | Bayside Board Co | Materials for kitchen joinery | 909.76
2026-07-27 | J-2604 | Waste removal | Skip-it Bins | Waste removal for built-in wardrobes | 565.84
2026-07-29 | J-2603 | Subcontractor | Spark Lane Electrical | Subcontractor for kitchen joinery | 434.51
2026-07-29 | J-2603 | Waste removal | Skip-it Bins | Waste removal for kitchen joinery | 113.5
2026-07-29 | J-2603 | Equipment hire | Hirepoint | Equipment hire for kitchen joinery | 180.29
2026-07-29 | J-2603 | Equipment hire | Hirepoint | Equipment hire for kitchen joinery | 148.45
2026-07-29 | J-2604 | Materials | Timberline Supplies | Materials for built-in wardrobes | 1038.61
2026-07-30 | J-2604 | Subcontractor | Spark Lane Electrical | Subcontractor for built-in wardrobes | 289.82
2026-07-31 | J-2603 | Materials | Hardwarehouse | Materials for kitchen joinery | 1086.21
2026-08-01 | J-2603 | Equipment hire | Hirepoint | Equipment hire for kitchen joinery | 547.53
2026-08-01 | J-2603 | Materials | Timberline Supplies | Materials for kitchen joinery | 514.89
2026-08-02 | J-2603 | Materials | Bayside Board Co | Materials for kitchen joinery | 239.33
2026-08-02 | J-2604 | Materials | Bayside Board Co | Materials for built-in wardrobes | 634.64
2026-08-03 | J-2603 | Subcontractor | Spark Lane Electrical | Subcontractor for kitchen joinery | 540.29
2026-08-03 | J-2604 | Travel & parking | Parking / tolls | Travel & parking for built-in wardrobes | 584.04
2026-08-03 | J-2605 | Equipment hire | Hirepoint | Equipment hire for fencing | 77.76
2026-08-03 | J-2605 | Equipment hire | Hirepoint | Equipment hire for fencing | 98.58
2026-08-05 | J-2603 | Materials | Bayside Board Co | Materials for kitchen joinery | 167.7
2026-08-06 | J-2604 | Materials | Hardwarehouse | Materials for built-in wardrobes | 800.05
2026-08-06 | J-2605 | Materials | Timberline Supplies | Materials for fencing | 1645.98
2026-08-06 | J-2605 | Materials | Bayside Board Co | Materials for fencing | 465.68
2026-08-08 | J-2603 | Materials | Timberline Supplies | Materials for kitchen joinery | 1512.08
2026-08-10 | J-2606 | Materials | Bayside Board Co | Materials for bathroom vanity | 1695.35
2026-08-13 | J-2606 | Materials | Hardwarehouse | Materials for bathroom vanity | 603.65
2026-08-17 | J-2607 | Materials | Timberline Supplies | Materials for repairs | 427.5
2026-08-24 | J-2608 | Waste removal | Skip-it Bins | Waste removal for deck | 649.72
2026-08-26 | J-2608 | Materials | Timberline Supplies | Materials for deck | 550.5
2026-08-29 | J-2608 | Travel & parking | Parking / tolls | Travel & parking for deck | 175.06
2026-08-30 | J-2608 | Materials | Timberline Supplies | Materials for deck | 855.91
2026-08-30 | J-2608 | Materials | Timberline Supplies | Materials for deck | 673.58
2026-08-31 | J-2609 | Materials | Hardwarehouse | Materials for built-in wardrobes | 657.17
2026-08-31 | J-2609 | Materials | Bayside Board Co | Materials for built-in wardrobes | 1290.13
2026-09-01 | J-2608 | Materials | Hardwarehouse | Materials for deck | 446.99
2026-09-01 | J-2608 | Waste removal | Skip-it Bins | Waste removal for deck | 267.13
2026-09-01 | J-2608 | Materials | Bayside Board Co | Materials for deck | 346.29
2026-09-01 | J-2609 | Materials | Timberline Supplies | Materials for built-in wardrobes | 692.7
2026-09-02 | J-2608 | Materials | Timberline Supplies | Materials for deck | 1397.77
2026-09-04 | J-2608 | Travel & parking | Parking / tolls | Travel & parking for deck | 343.28
2026-09-04 | J-2608 | Waste removal | Skip-it Bins | Waste removal for deck | 298.94
2026-09-07 | J-2608 | Materials | Timberline Supplies | Materials for deck | 274.52
2026-09-07 | J-2610 | Materials | Timberline Supplies | Materials for kitchen joinery | 1426.82
2026-09-07 | J-2610 | Materials | Timberline Supplies | Materials for kitchen joinery | 1594.7
2026-09-07 | J-2610 | Materials | Bayside Board Co | Materials for kitchen joinery | 1444.07
2026-09-08 | J-2608 | Subcontractor | Spark Lane Electrical | Subcontractor for deck | 602.31
2026-09-10 | J-2610 | Materials | Hardwarehouse | Materials for kitchen joinery | 1408.56
2026-09-10 | J-2610 | Materials | Bayside Board Co | Materials for kitchen joinery | 138.33
2026-09-12 | J-2610 | Materials | Hardwarehouse | Materials for kitchen joinery | 311.52

## Lists
Status | Cost category | Staff | Cost rate /hr | Job type | Budget labour rate /hr
Quoted | Materials | Sam R. (lead carpenter) | 58 | Deck | 42
Booked | Subcontractor | Ari K. (carpenter) | 44 | Pergola
In progress | Equipment hire | Jo P. (apprentice) | 27 | Kitchen joinery
Complete | Travel & parking | Dev M. (labourer) | 34 | Built-in wardrobes
Invoiced | Waste removal |  |  | Fencing
Bathroom vanity
Repairs

## Checks
Data checks (live)
# | Check | Value A | Value B | Result
1 | Timesheet hours = hours on Jobs tab | 466 | 466 | PASS
2 | Timesheet labour cost = labour cost on Jobs tab | 19458 | 19458 | PASS
3 | Cost log total = materials & other on Jobs tab | 48217.5 | 48217.5 | PASS
4 | Timesheet rows with an unknown Job ID | 0 | 0 | PASS
5 | Cost rows with an unknown Job ID | 0 | 0 | PASS
6 | Timesheet rows with no cost rate (unknown staff) | 0 | 0 | PASS
7 | Dashboard category total = all job costs | 67675.5 | 67675.5 | PASS
8 | Duplicate Job IDs | 0 | 0 | PASS
| Checks passed | 8 of 8

## How to use
How to use this tracker (Sample project, placeholder data)
1. Add a job on the Jobs tab: type the client, pick a Job type and Status from the drop-downs, enter the quote and budget (yellow cells).
2. Log hours on the Timesheet tab: pick the Job ID and staff member from the drop-downs; the cost rate fills in from the Lists tab.
3. Log materials and other costs on the Costs tab: pick the Job ID and category from the drop-downs.
4. The Jobs tab and the Dashboard update straight away: actual cost, gross profit, margin %, budget used % and a flag.
Flags: Over budget (actual cost above budget cost), At risk (90%+ of budget used on a job still running), On track.
5. Staff cost rates, categories, statuses and the budget labour rate live on the Lists tab.
6. The Checks tab confirms the timesheet and cost log tie back to the Jobs tab and that no row uses an unknown Job ID.